## Cover Page
Clinical Safety Hazard Log - Clinical Decision Support FHIR API v1.1
Programme | Urgent and Emergency Care Digital Integration | Document Record ID Key
Sub-Prog / Project
Prog. Director | Tim Magor | Status | CSG endorsed
Owner | Lee Montgomery | Version | 1
Author | Julie Harris | Version Date | 2020-01-15
Clinical Safety Hazard Log - Clinical Decision Support FHIR API
Document Purpose
Copyright © 2019, Health and Social Care Information Centre. NHS Digital is the trading name of the Health and Social Care Information Centre.All Rights Reserved.

## Version History
Amendment History
Version | Amendment History
0.1 | First draft Hazard Log
0.2 | Updated with CDS API v1.1 updates
0.3 | Updated post Hazard workshop
0.4 | CSO approved
1 | CSG endorsed
Reviewers
This document must be reviewed by the following:
Name | Title / Responsibility | Date | Version
Reviewer name | Date | Version
David Waters | Technical Architect | 2020-01-08 | 1
Louis Coles | Programme Manager | 2020-01-08 | 1
Charles Olowosuko | Safety Engineer | 2019-07-26 | 1
Afzal Mufti | Business Analyst | 2020-01-08 | 1
Lee Montgomery | Clinical Lead and CSO UECDI | 2019-12-20 | 0.2
Bruno Tchek | Safety Engineer | 2019-12-20 | 1
Approved
This document must be approved by the following:
Name | Title / Responsibility | Date | Version
Martin O'Keeffe | UEC Clinical Safety Officer | 2020-01-08 | 1
Distribution
UEC DI Programme, NHS Digital Clinical Safety Group, UEC Provider Organisations, UEC Provider System suppliers.
Document Status:
The controlled copy of this document is maintained in the NHS Digital corporate network. Any copies of this document held outside of that area, in whatever format (e.g. paper, email attachment), are considered to have passed out of control and should be checked for currency and validity.

## Hazard Log
Num | Hazard Name | Hazard Description | Potential Clinical Impact | Existing Controls | Possible Causes | Initial Consequence | Initial Likelihood | Initial Risk | Additional controls | Control type | Control owner | Action | Action status | Residual Consequence | Residual Likelihood | Residual Risk
H01 | Absent or incomplete triage | This hazard relates to the absence of triage. This includes incomplete triage that does not lead to an outcome and the absence of care advice either at the end of or during triage. | In the absence of triage there is likely to be a delay in the delivery of care whilst the patient or HCP seeks alternative advice. If care advice is absent it may not be detectable, particularly if it is single piece of advice missing from a list. The severity of the consequence will be have a direct relationship to the acuity of the patient's clinical need. | Where an HCP is present (e.g. NHS 111, ED, OOH, UTC) they may triage the patient using their clinical knowledge or follow local policies and procedures. In the situation of online self-triage a patient may use an alternative triage site, call NHS 111/999 or directly contact/ visit a UEC care service (e.g. GP, OOH, ED). | 0101 Messaging failure | Major | Medium | 3 | 010101 The CDS API implementation guide to provide guidance on alerts, timeouts and retry mechanisms for both initiating and responding systems to ensure that messaging failures are detected and managed appropriately. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0101 Messaging failure | Major | Medium | 3 | 010102 Deployment organisations to put service desk processes in place to manage failed message queues. | Process | Deploying organisation | Risk transferred in Hazard Log | closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0101 Messaging failure | Major | Medium | 3 | 010103 The CDS API guidance to define error codes and recommended system behaviour where appropriate. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0101 Messaging failure | Major | Medium | 3 | 010104 Conformance approach to include verification of the appropriate use of error codes due to messaging failure. | Test | NHSD | Validate conformance approach | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0101 Messaging failure | Major | Medium | 3 | 010105 CDS API guidance to specify pre-requisites for CDS API FHIR servers. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 101 Messaging failure | Major | Medium | 3 | 010106 Conformance approach to include verification of pre-requisites for CDS API FHIR servers. | Test | NHSD | Validate conformance approach | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 101 Messaging failure | Major | Medium | 3 | 010107 The restful nature of the API means that and EMS can recover from a temporary interruption to messaging and continue from where it left off. This is because when the EMS invokes a ServiceDefinition.$evaluate operation it references a QuestionnaireResponse and any previous assertions (Observation resources) for the CDSS to evaluate. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0101 Messaging failure | Major | Medium | 3 | 010108 Conformance approach to include verification that when the EMS invokes a ServiceDefinition.$evaluate operation it references a QuestionnaireResponse and ALL previous assertions (Observation resources) for the CDSS to evaluate. This to include negative testing and interruptions. | Test | NHSD | Validate conformance approach | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0102 Malicious attack | Major | Medium | 3 | 010201 The CDS API guidance to provide guidelines relating to the NHS Digital approach to security | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0102 Malicious attack | Major | Medium | 3 | 010202 Deploying organisation to undertake security testing of their deployment. | Test | Deploying organisation | Risk transferred in Hazard Log | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0103 Clinical decision logic to support the triage of a given presenting complaint cannot be found. | Major | Medium | 3 | 010301 Deploying healthcare organisations to ensure through clinical integrity checking that deployed CDSS(s) cover presenting complaints appropriate for the care setting in which they are deployed. | Test | Deploying organisation | Risk transferred in Hazard Log | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0103 Clinical decision logic to support the triage of a given presenting complaint cannot be found. | Major | Medium | 3 | 010302 CDS API guidance to ensure that each CDSS can cope with situations where nothing is known about the patient at the start of triage. i.e. state that each CDSS MUST publish a ServiceDefinition with a 'NULL' Trigger | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0103 Clinical decision logic to support the triage of a given presenting complaint cannot be found. | Major | Medium | 3 | 010303 Conformance approach to include verification that each CDSS has published a ServiceDefinition with a 'NULL' Trigger | Test | NHSD | Validate conformance approach | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0103 Clinical decision logic to support the triage of a given presenting complaint cannot be found. | Major | Medium | 3 | 010304 CDS API guidance to specify the ServiceDefinition resource to enable CDSS suppliers to describe which decisions the CDS is able to provide support for, under what circumstances the CDS is valid, and the information needed to render the decision. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0103 Clinical decision logic to support the triage of a given presenting complaint cannot be found. | Major | Medium | 3 | 010305 Conformance approach to include CDSS supplier testing to ensure that all CDSS ServiceDefinitions are conformant with CDS API guidance | Test | NHSD | Validate conformance approach | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0103 Clinical decision logic to support the triage of a given presenting complaint cannot be found. | Major | Medium | 3 | 010306 CDS API guidance to specify how an EMS searches for and selects an appropriate ServiceDefinition for the patient's presenting complaint and other known relevant observations. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0103 Clinical decision logic to support the triage of a given presenting complaint cannot be found. | Major | Medium | 3 | 010307 Conformance approach to include verification that the EMS can: Initiate the selection of a ServiceDefinition Initiate the evaluation of a ServiceDefinition | Test | NHSD | Validate conformance approach | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0103 Clinical decision logic to support the triage of a given presenting complaint cannot be found. | Major | Medium | 3 | 010308 In order for Clinical Decision Logic to be invoked all live Service Definitions urls MUST be populated with the address at which the ServiceDefinition is published which MUST be globally unique. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0104 Triage fails to complete | Major | Medium | 3 | 010401 Guidance to be provided to CDSS suppliers to ensure that all Service Definitions end in the provision of Care Advice, a Referral Request or point to another ServiceDefinition. | Design | NHSD | Validate CDS API usage guide | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0104 Triage fails to complete | Major | Medium | 3 | 010402 Conformance approach to include verification that all ServiceDefinitions end in a Result or to point to another ServiceDefinition | Test | NHSD | Validate conformance approach | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0104 Triage fails to complete | Major | Medium | 3 | 010403 CDS API implementation guidance to describe error codes and expected EMS or CDSS behaviour for ALL validation errors. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0104 Triage fails to complete | Major | Medium | 3 | 010404 Guidance to be provided to ensure that Service Definitions that end with a redirection do not point to Service Definitions that redirect to the initiating Service Definition either directly or indirectly. | Training | NHSD | Validate CDS API usage guide | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0105 Presenting complaint is not coded correctly | Major | Medium | 3 | 010501 The CDSS is responsible for ensuring that the presenting complaint is coded in a conformant manner. This may be by use of Natural Language processing. | Design | CDSS supplier | Risk transferred in Hazard Log | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0106 Presenting complaint is not coded correctly | Major | Medium | 3 | 010502 EMS suppliers to consider system behaviour to ensure that End Users can validate the coded presenting complaint during their Clinical Safety activities in accordance with DCB0129 | Design | EMS supplier | Risk transferred in Hazard Log | Closed | Major | Very low | 2
H01 | Absent or incomplete triage |  |  |  | 0106 This Release does not support the triage of an incident with an unknown number of patients. | Major | Medium | 3 | 010601 Guidance to state that triage of an incident with an unknown number of patients.is out of scope for this Release. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage | This hazard relates to an inappropriate triage outcome for the patient's presenting complaint. This includes a triage outcome in an inappropriate format and inappropriate advice given at the end of or during triage. | An inappropriate triage outcome may lead to a patient being given the wrong advice which may lead to a delay in the delivery of care, or the delivery of inappropriate care which may lead to harm | Where an HCP is undertaking the CDSS supported triage (e.g. NHS 111, ED, OOH, UTC) they MAY recognise that the triage advice is inappropriate and triage the patient using their clinical knowledge or follow local policies and procedures. In the situation of online self-triage, a patient is less likely to recognise that the triage advice is inappropriate, but if they do they may use an alternative triage site, call NHS 111/999 or directly contact/ visit a UEC care service (e.g. GP, OOH, ED). | 0201 Wrong clinical decision support logic (ServiceDefinition) used for patient's presenting complaint | Major | Medium | 3 | 020101 CDSS supplier is responsible for publishing the ServiceDefinition resource which describes which decisions the CDSS is able to provide support for, under what circumstances the CDS is valid, and the information needed to render the decision. This must be conformant with the CDS API ServiceDefinition Implementation Guidance. | Design | CDSS supplier | Risk transferred in Hazard Log | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0201 Wrong clinical decision support logic (ServiceDefinition) used for patient's presenting complaint | Major | Medium | 3 | 020102 The ServiceDefinition.purpose which describes why this service definition is defined MUST be populated. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0202 Errors in Service Definition | Major | Medium | 3 | 020201 It is assumed that CDSS suppliers will undertake testing to ensure that selection of a ServiceDefinition launches the expected triage logic | Test | CDSS supplier | Risk transferred in Hazard Log | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0201 Wrong clinical decision support logic (ServiceDefinition) used for patient's presenting complaint | Major | Medium | 3 | 020103 EMS suppliers to consider system behaviour to ensure that End Users can validate that the CDS is appropriate for the patient's presenting complaint in their Clinical Safety activities. | Design | EMS supplier | Risk transferred in Hazard Log | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0203 Test Service definition gets into Live | Major | Medium | 3 | 020301 CDSS suppliers' governance processes to include the safe publication of Service Definitions. | Design | Supplier | Risk transferred in Hazard Log | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0203 Test Service definition gets into Live | Major | Medium | 3 | 020301 Conformance approach to include verification that only Service Definitions with a status of 'Active' can be used in Live. | Test | NHSD | Validate conformance approach | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0203 Test Service definition gets into Live | Major | Medium | 3 | 020302 Deploying service providers' governance processes to include the safe publication of Service Definitions. | Design | Deploying organisation | Risk transferred in Hazard Log | Closed | Major | Very low | 2
[5 empty] | 0203 Test Service definition gets into Live | Major | Medium | 3 | 020303 CDS API implementation guide states that only Service Definitions with a status of 'Active' can be used in Live but provides other statuses for ServiceDefinitions in test. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0204 Observations from another patient are consumed by the CDSS | Major | Medium | 3 | 020401 The CDSS MUST populate the Observation.subject with the ServiceDefinition.$evaluate.patient posted by the EMS. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0204 Observations from another patient are consumed by the CDSS | Major | Medium | 3 | 020402 The EMS is responsible for maintaining patient context | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0204 Observations from another patient are consumed by the CDSS | Major | Medium | 3 | 020402 CDSS MUST only consume assertions where the Observation.subject matches the ServiceDefinition.$evaluate.patient | Design | Supplier | Risk transferred in Hazard Log | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0205 Assertions from a different encounter (same patient) are consumed by the CDSS in error. (This excludes intended use of assertions from different encounters e.g. Patient Medical History) | Major | Medium | 3 | 020501 The EMS is responsible for maintaining encounter context. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0205 Assertions from a different encounter (same patient) are consumed by the CDSS in error. (This excludes intended use of assertions from different encounters e.g. Patient Medical History) | Major | Medium | 3 | 020502 CDSS to populate the Observation.context with the ServiceDefinition.$evaluate.encounter posted by the EMS | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0205 Assertions from a different encounter (same patient) are consumed by the CDSS in error. (This excludes intended use of assertions from different encounters e.g. Patient Medical History) | Major | Medium | 3 | 020402 CDSS MUST consider the Observation.context in its logic. | Design | CDSS supplier | Risk transferred in Hazard Log | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0206 Time dependant Observations that are no longer current are consumed by the CDSS | Major | Medium | 3 | 020601 The ServiceDefinition.dataRequirements MUST be populated with the set of machine-processable assertions which the CDSS logic requires in order to render the response fully. These must be specified to a level of detail appropriate for the CDSS logic and MUST include all meta data required to support the decision. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0206 Time dependant Observations that are no longer current are consumed by the CDSS | Major | Medium | 3 | 020602 Each Observation Resource to include the time/date that the observation was made. This should based on the QuestionnaireResponse.authored entry from the EMS. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0206 Time dependant Observations that are no longer current are consumed by the CDSS | Major | Medium | 3 | 020603 Each Observation Resource to include an 'effective' date/time. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0206 Time dependant Observations that are no longer current are consumed by the CDSS | Major | Medium | 3 | 020604 CDSS MUST consider the Observation temporal meta data in its logic before consuming it to drive system behaviour (e.g. skipping questions, validating responses). | Design | Supplier | Risk transferred in Hazard Log | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0206 Time dependant Observations that are no longer current are consumed by the CDSS | Major | Medium | 3 | 020603 Conformance testing to ensure that Observations that have exceeded their 'effective' date/time are not consumed by CDSSs. | Test | NHSD | Validate conformance approach | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0207 Assertion from third party clinical content consumed by CDSS is not equivalent to the same assertion recorded locally. e.g. prompted from a question with a different clinical intent to the local question | Major | Medium | 3 | 020701 ServiceDefinition.dataRequirements MUST be populated with the set of machine-processable assertions which the CDSS logic requires in order to render the response fully. This MUST include all meta data required to support the decision e.g. Codes and Values. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0207 Assertion from third party clinical content consumed by CDSS is not equivalent to the same assertion recorded locally. e.g. prompted from a question with a different clinical intent to the local question | Major | Medium | 3 | 020702 The CDSS supplier is responsible for creating coded assertions that accurately reflect the clinical meaning of the answers provided in the QuestionnaireResponse to the questions detailed in the associated Questionnaire. | Design | Supplier | Risk transferred in Hazard Log | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0207 Assertion from third party clinical content consumed by CDSS is not equivalent to the same assertion recorded locally. e.g. prompted from a question with a different clinical intent to the local question | Major | Medium | 3 | 020703 The CDS API shall send the Questionnaire and Response that prompted an Assertion to provide additional information. This is in the GuidanceResponse. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0208 Observation made (assertion) is not part of the Value Set | Major | Medium | 3 | 020801 The binding strength of the ValueSets associated with Observation.code and Observation.value to support values outside of those Value Sets. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0208 Observation made (assertion) is not part of the Value Set | Major | Medium | 3 | 020801 CDS API owner to have a process in place for healthcare providers and system suppliers to suggest additional values for value sets, for the value sets to be updated and changes communicated to stakeholders. | Process | NHSD | Validate CDS API usage guide | Deferred to version 2.0 | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0208 Observation made (assertion) is not part of the Value Set | Major | Medium | 3 | 020802 Conformance approach to include verification that CDSS Observations (assertions) are conformant with the defined Value Sets | Test | NHSD | Validate conformance approach | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0208 Observation made (assertion) is not part of the Value Set | Major | Medium | 3 | 020803 Value Set definition to be undertaken as part of the Curation Process. This must be undertaken by a multi disciplinary team and include a full Clinical review to ensure accuracy and completeness. | Process | NHSD | Review process to support updates to Value Sets | Deferred to version 2.0 | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0208 Observation made (assertion) is not part of the Value Set | Major | Medium | 3 | 020804 FHIR Curation process MUST include a formal change control process that ensures breaking changes are not made to published (curated) ValueSets that are used by the CDS API without agreement from the UEC DI programme team. | Process | NHSD/ InterOpen | Open |  | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0209 Failure to branch to more appropriate question set E.g. Back pain to back injury | Major | Medium | 3 | 020901 CDS API supports redirection to another Service Definition through the GuidanceResponse.dataRequirement element which isused to carry a description of the data required by the EMS to enable it to select the new ServiceDefinition as directed by the CDSS. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0209 Failure to branch to more appropriate question set E.g. Back pain to back injury | Major | Medium | 3 | 020902 Conformance approach to include verification of logical completeness of CDSS Service Definitions. E.g. If SD1 ends with SD3 and Result 4 they have to exist. | Test | NHSD | Validate conformance approach | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0210 The wrong version of an assertion is consumed by the CDS API. E.g. An observation/assertion that has been subsequently amended. | Major | Medium | 3 | 021001 Each assertion to include an effective (period). | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0210 The wrong version of an assertion is consumed by the CDS API. E.g. An observation/assertion that has been subsequently amended. | Major | Medium | 3 | 021002 The FHIR resource server is responsible for storing each version of an assertion within a patient encounter and for determining which version is passed to the CDS API in the ServiceDefinition$Evaluate at any point in the encounter. | Design | Deploying organisation | Validate CDS API usage guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0210 The wrong version of an assertion is consumed by the CDS API. E.g. An observation/assertion that has been subsequently amended. | Major | Medium | 3 | 021003 Each assertion has a Reference ID which remains the same when the status is changed | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0210 The wrong version of an assertion is consumed by the CDS API. E.g. An observation/assertion that has been subsequently amended. | Major | Medium | 3 | 021004 Conformance approach to include verification that the EMS passes the latest version of an assertion within an encounter to the CDS API in the ServiceDefinition$Evaluate. | Test | NHSD | Validate conformance approach | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0210 The wrong version of an assertion is consumed by the CDS API. E.g. An observation/assertion that has been subsequently amended. | Major | Medium | 3 | 021005 When the CDSS consumes an observation within an encounter and updates it, it updates the status to AMENDED | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0211 Presenting complaint incorrect. E.g. CDSS codes presenting complaint incorrectly by. NLP failure. | Major | Medium | 3 | 021101 The ServiceDefnition.title, .description and .purpose are populated with details about the selected CDS logic. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
[5 empty] | 0211 Presenting complaint incorrect. E.g. CDSS codes presenting complaint incorrectly by. NLP failure. | Major | Medium | 3 | 021102 The CDSS is responsible for correctly coding the presenting complaint and for the CDS logic associated with that. | Design | CDSS supplier | Risk transferred in Hazard Log | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0211 Presenting complaint incorrect. E.g. CDSS codes presenting complaint incorrectly by. NLP failure. | Major | Medium | 3 | 021103 Conformance approach to include verification that CDSS supplier has undertaken testing to ensure accurate coding of presenting complaint, this must include NLP testing if this is used. | Test | NHSD | Validate conformance approach | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0211 Presenting complaint incorrect. E.g. CDSS codes presenting complaint incorrectly by. NLP failure. | Major | Medium | 3 | 021104 EMS suppliers will assess the risk of the display of ServiceDefnition.title, .description and .purpose to end users in their Clinical Safety activities. | Design | EMS supplier | Risk transferred in Hazard Log | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0212 CDS inappropriate for the EMS User Role e.g. Patient, non clinical personnel, generalist clinician, specialist | Major | Medium | 3 | 021201 The ServiceDefinition,useContext to be populated with the context the content is intended to support. This can include user role. If no useContext is specified, this means the ServiceDefinition is appropriate for any useContext. | Design | Supplier | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0212 CDS inappropriate for the EMS User Role e.g. Patient, non clinical personnel, generalist clinician, specialist | Major | Medium | 3 | 021202 Guidance to be provided about use of ServiceDefinition.useContext and/or Questionnaire.useContext to support filtering of Service Definitions user role. | Design | Supplier | Validate CDS API usage guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0212 CDS inappropriate for the EMS User Role e.g. Patient, non clinical personnel, generalist clinician, specialist | Major | Medium | 3 | 021203 CDS API Implementation guide to state that the EMS is responsible for sending the User Role, where appropriate, in the useContext in each $evaluate interaction. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0213 CDS inappropriate for the Service setting e.g. An ED Reception desk for face to face triage will not require Ambulance triage outcomes. | Major | Medium | 3 | 021301 The ServiceDefinition,useContext to be populated with the context the content is intended to support. This can include service type. If no useContext is specified, this means the ServiceDefinition is appropriate for any useContext. | Design | Supplier | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0213 CDS inappropriate for the Service setting e.g. An ED Reception desk for face to face triage will not require Ambulance triage outcomes. | Major | Medium | 3 | 021302 Guidance to be provided about use of ServiceDefinition.useContext and/or Questionnaire.useContext to support filtering of Service Definitions by Service Type. | Design | Supplier | Validate CDS API usage guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0213 CDS inappropriate for the Service setting e.g. An ED Reception desk for face to face triage will not require Ambulance triage outcomes. | Major | Medium | 3 | 021303 The EMS is responsible for setting the Service Type context | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0214 CDS inappropriate for change in environment factors (e.g. Localised increased pollution, heatwave, flu epidemic, Ebola outbreak, CBRN incident) | Major | Medium | 3 | 021401 The ServiceDefinition,useContext to be populated with the context the content is intended to support. This can include specified environmental factors. If no useContext is specified, this means the ServiceDefinition is appropriate for any useContext. | Design | Supplier | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0214 CDS inappropriate for change in environment factors (e.g. Localised increased pollution, heatwave, flu epidemic, Ebola outbreak, CBRN incident) | Major | Medium | 3 | 021402 Guidance to be provided about use of ServiceDefinition.useContext and/or Questionnaire.useContext to support filtering of Service Definitions by environmental factors. | Design | Supplier | Validate CDS API usage guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0214 CDS inappropriate for change in environment factors (e.g. Localised increased pollution, heatwave, flu epidemic, Ebola outbreak, CBRN incident) | Major | Medium | 3 | 021403 The EMS is responsible for setting useContext.This may include specific environmental factors. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0215 Default response to a Questionnaire, that does not match the actual response, is inadvertently accepted by EMS user. | Major | Medium | 3 | 021501 Implementation guidance to state that default questionnaire responses MUST NOT be populated by the CDSS in the Questionnare.item item.initial[x] | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0216 Secondary concerns may not be recognised. | Major | Medium | 3 | 021601 Review of the use of ReferralRequest.supportingInformation element for recording secondary concerns and how it might be used to drive Directory searches. | Design | NHSD | Validate CDS API implementation guide | Deferred to version 2.0 | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0217 Questions may become ambiguous when more than one Service Definition is running concurrently. E.g. Head ache and leg pain and a question of how much does it hurt or how long have you had it? | Major | Medium | 3 | 021701 Provide guidance on the design of questions and permitted responses that take into account that multiple ServiceDefinitions may run concurrently. | Design | NHSD | Validate CDS API usage guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0217 Questions may become ambiguous when more than one Service Definition is running concurrently. E.g. Head ache and leg pain and a question of how much does it hurt or how long have you had it? | Major | Medium | 3 | 021702 CDSS supplier to ensure that all questions and permitted responses are self contained and self explanatory | Design | CDSS supplier | Risk transferred in Hazard Log | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0218 Notes made by Clinicians are not taken into consideration by the CDSS. | Major | Medium | 3 | 021801 Guidance to be provided to state that notes made by EMS users are not taken into consideration by the CDSS. | Design | NHSD | Validate CDS API usage guide | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0218 Notes made by Clinicians are not taken into consideration by the CDSS. | Major | Medium | 3 | 021802 Assumed control that EMS suppliers will assess the risk of providing notes fields that are not taken into consideration by the CDSS. | Design | EMS supplier | Risk transferred in Hazard Log | Closed | Major | Very low | 2
H02 | Inappropriate triage |  |  |  | 0211 Message corruption | Major | Medium | 3 | 21601The CDS API guidance to define error codes and recommended system behaviour where appropriate. | Design | NHSD | Validate CDS API implementation guide | Closed | Major | Very low | 2
H03 | Triage outcome information misleads HCPs | This hazard relates to triage information created by the CDS API misleading HCPs who may be validating triage initiated by non-clinical staff. | If a triage outcome misleads HCPs it my contribute to them making an inappropriate decision about the patient's clinical care. This may lead to a delay in the delivery of care or the delivery of inappropriate care. | HCPs will use their clinical judgement to inform their decision and validate any information that looks in doubt. | 0301 Lack of clarity if an observation/assertion has been amended at the time of entry or updated at a later point in the journey, potentially due to patient deterioration as the CDSS will assign them both a status of amended. | Significant | Medium | 2 | 030101 Each assertion to have an effective (period). | Design | NHSD | Validate CDS API implementation guide | Closed | Significant | Low | 2
H03 | Triage outcome information misleads HCPs |  |  |  | 0301 Lack of clarity if an observation/assertion has been amended at the time of entry or updated at a later point in the journey, potentially due to patient deterioration as the CDSS will assign them both a status of amended. | Significant | Medium | 2 | 030102 The FHIR resource server is responsible for storing each version of an assertion within a patient encounter and for determining which version is passed to the CDS API in the ServiceDefinition$Evaluate at any point in the encounter. | Design | NHSD | Validate CDS API implementation guide | Closed | Significant | Low | 2
H03 | Triage outcome information misleads HCPs |  |  |  | 0301 Lack of clarity if an observation/assertion has been amended at the time of entry or updated at a later point in the journey, potentially due to patient deterioration as the CDSS will assign them both a status of amended | Significant | Medium | 2 | 030103 If a question is asked again and a duplicate assertion is created the assertion will have a different Reference ID. | Design | NHSD | Validate CDS API implementation guide | Closed | Significant | Low | 2
H03 | Triage outcome information misleads HCPs |  |  |  | 0302 Use of clinical qualifiers mislead. E.g. If the observation code is 'Haemorrhage' and the qualifier is 'absent' and the observation code is taken in isolation, it may lead to inappropriate clinical decisions by clinicians. | Significant | Medium | 2 | 030201 Implementation guidance to ensure that clinical meaning is preserved for all clinical resources in a consistent manner inline with NHS terminology standards e.g. SNOMED CT SCCI034 | Design | CDSS supplier | Risk transferred in Hazard Log | Closed | Significant | Low | 2
H03 | Triage outcome information misleads HCPs |  |  |  | 0302 Use of clinical qualifiers mislead. E.g. If the observation code is 'Haemorrhage' and the qualifier is 'absent' and the observation code is taken in isolation, it may lead to inappropriate clinical decisions by clinicians. | Significant | Medium | 2 | 030202 CDSS suppliers are responsible for ensuring that that the assertions (generally Observation resources) are coded to preserve the clinical meaning of the response. This includes the use of relevant clinical qualifiers e.g. Observation value | Design | CDSS supplier | Risk transferred in Hazard Log | Closed | Significant | Low | 2
H03 | Triage outcome information misleads HCPs |  |  |  | 0302 Use of clinical qualifiers mislead. E.g. If the observation code is 'Haemorrhage' and the qualifier is 'absent' and the observation code is taken in isolation, it may lead to inappropriate clinical decisions by clinicians. | Significant | Medium | 2 | 030203 CDSS suppliers are responsible for ensuring that that Chief and Secondary Concerns (Condition resources) are coded in a way that that conveys their clinical meaning and can be consumed by downstream systems (e.g. EMS, Directory Services) . This includes the use of relevant clinical qualifiers. | Design | CDSS supplier | Risk transferred in Hazard Log | Closed | Significant | Low | 2
H03 | Triage outcome information misleads HCPs |  |  |  | 0302 Use of clinical qualifiers mislead. E.g. If the observation code is 'Haemorrhage' and the qualifier is 'absent' and the observation code is taken in isolation, it may lead to inappropriate clinical decisions by clinicians. | Significant | Medium | 2 | 030204 Where assertions are stored, displayed or communicated by the EMS they must include all elements required to preserve clinical meaning. | Design | EMS supplier | Risk transferred in Hazard Log | Closed | Significant | Low | 2
H03 | Triage outcome information misleads HCPs |  |  |  | 0302 Use of clinical qualifiers mislead. E.g. If the observation code is 'Haemorrhage' and the qualifier is 'absent' and the observation code is taken in isolation, it may lead to inappropriate clinical decisions by clinicians. | Significant | Medium | 2 | 030205 Service Providers are responsible for undertaking assurance of the CDSS to ensure that the Observation.codes created from a QuestionnaireResponse reflects its meaning. |  |  |  |  | Significant | Low | 2
H03 | Triage outcome information misleads HCPs |  |  |  | 0303 If allergic causative agents (allergens) of medicine allergies are recorded using Observation resources with SNOMED CT finding codes, other CDSS may not be able to use the code in prescribing decision support. | Significant | Medium | 2 | 030301 CDS API POCs, Alpha or Beta projects to explore the use of the FHIR Allergy resource which include the causative agent for assertions relating to allergy (e.g. Aspirin allergy). This to include a risk benefits analysis of using this as opposed to recording a clinical finding in an Observation resource, given that the allergy is likely to be one reported by the patient rather than being a confirmed allergy. | Design | NHSD | Review POCs, Alpha or Beta scope | Deferred to version 2.0 | Significant | Low | 2
H03 | Triage outcome information misleads HCPs |  |  |  | 0304 If assertions relating to medications are recorded using the Observation resource with SNOMED CT finding codes, other CDSS may not be able to use the code in prescribing decision support. | Significant | Medium | 2 | 030401 CDS API POCs, Alpha or Beta projects to explore the use of FHIR Medication resources with dm+d medicine codes (e.g. taking glyceryl trinitrate). This to include a risk benefits analysis of using this as opposed to recording a clinical finding in an Observation resource, given that the medication is likely to be one reported by the patient rather than being a confirmed administration. | Design | NHSD | Review POCs, Alpha or Beta scope | Deferred to version 2.0 | Significant | Low | 2
H03 | Triage outcome information misleads HCPs |  |  |  | 0305 HCP unclear of certainty of assertions. E.g. Patient states that they have fever but this is not confimed with a temperature measurement. Chief concern is Pneumonia but this is only suspected from the patient's responses during triage and is not confirmed. | Significant | Medium | 2 | 030501 CDS API guidance to ensure that coding model for assertions includes the appropriate modifiers to indicate the level of confidence. E.g. Patient reported fever, Suspected chief concern, | Design | NHSD | Validate CDS API implementation guide | Closed | Significant | Low | 2
H04 | Failure to identify an appropriate service using the CDS API triage outcome | This hazard relates to the failure of the use of information provided in the triage outcome to search Service Directories to identify a Service that can meet the patient's needs within an appropriate timeframe. This includes the identification of an ambulance resource with the appropriate priority level. (Note: this does not include the recommendation of a service with a higher acuity than is required as this would meet the patient's needs, albeit inefficiently for the NHS) | If the triage outcome information cannot be used to identify a suitable service or ambulance resource to meet the patient's needs in an appropriate timeframe, there will be a delay in the delivery of care which may lead to harm. The consequence of the delay will be dependent on the acuity of the patient's need and the length of the delay. | Users could access standalone directory services and contact services directly. Patients or UEC providers can ring 999 for an ambulance. | 0401 Triage outcome resource elements that could be used to drive a Service Directory search are not present. | Considerable | Low | 2 | 040101 CDS API design process to include a multidisciplinary review of all triage outcome information included in the ReferralRequest to ensure it can drive a Directory search to identify a service that meets the patient's needs. This must consider cardinality and guidance to be provided to CDS API implementors regarding the presence (single and multiple) and absence of this data. Reviewers must include system suppliers, service providers and Directory Service representatives. | Process | NHSD | Review as part of version 2.0 CDS API implementation guide | Deferred to version 2.0 | Considerable | Very low | 2
H04 | Failure to identify an appropriate service using the CDS API triage outcome |  |  |  | 0401 Triage outcome resource elements that could be used to drive a Service Directory search are not present. | Considerable | Low | 2 | 040402 CDS API POCs, Alpha or Beta projects to ascertain which ReferralRequest elements are required by Service Directories in order to identify a service to meet the patient's needs | Design | NHSD | Review as part of version 2.0 CDS API implementation guide | Deferred to version 2.0 | Considerable | Very low | 2
H04 | Failure to identify an appropriate service using the CDS API triage outcome |  |  |  | 0401 Triage outcome resource elements that could be used to drive a Service Directory search are not present. | Considerable | Low | 2 | 040403 Review of Directory Service standards to ensure that they are aligned with CDS API ReferalRequest elements and are not constrained to proprietary triage outcomes. | Design | NHSX | Review as part of version 2.0 CDS API implementation guide | Deferred to version 2.0 | Considerable | Very low | 2
H04 | Failure to identify an appropriate service using the CDS API triage outcome |  |  |  | 0401 Triage outcome resource elements that could be used to identify Ambulance Priority are not present | Considerable | Low | 2 | 040501 CDS API design process to include a multidisciplinary review of all triage outcome information included in the ReferralRequest to ensure that the triage outcome information is sufficient to map to Ambulance Priority Codes. This must consider cardinality and guidance to be provided to CDS API implementors regarding the presence (single and multiple) and absence of this data. Reviewers must include system suppliers, service providers and ambulance governance bodies representatives. | Process | NHSD | Review as part of version 2.0 CDS API implementation guide | Deferred to version 2.0 | Considerable | Very low | 2
H04 | Failure to identify an appropriate service using the CDS API triage outcome |  |  |  | 0401 Triage outcome resource elements that could be used to identify Ambulance Priority are not present | Considerable | Low | 2 | 040402 Review of ARP code mappings to triage outcomes to ensure that they are aligned with CDS API ReferalRequest elements and are not constrained to proprietary triage outcomes. | Design | NHSX | Review as part of version 2.0 CDS API implementation guide | Deferred to version 2.0 | Considerable | Very low | 2

## Risk Matrix
Likelihood | Very High | 3 | 4 | 4 | 5 | 5 | Severity Classification | Interpretation | No. of Patients Affected
| High | 2 | 3 | 3 | 4 | 5
| Medium | 2 | 2 | 3 | 3 | 4 | Catastrophic | Death | Multiple
| Low | 1 | 2 | 2 | 3 | 4 |  | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Multiple
| Very Low | 1 | 1 | 2 | 2 | 3
|  | Minor | Significant | Considerable | Major | Catastrophic | Major | Death | Single
|  | Severity | [5 empty] | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Single
| Likelihood Category | Interpretation | [5 empty] | Severe injury or severe incapacity from which recovery is expected in the short term | Multiple
| Very high | Certain or almost certain; highly likely to occur | [5 empty] | Severe psychological trauma | Multiple
| High | Not certain but very possible; reasonably expected to occur in the majority of cases |  |  |  |  | Considerable | Severe injury or severe incapacity from which recovery is expected in the short term | Single
| Medium | Possible | [5 empty] | Severe psychological trauma | Single
| Low | Could occur but in the great majority of occasions will not | [5 empty] | Minor injury or injuries from which recovery is not expected in the short term. | Multiple
| Very low | Negligible or nearly negligible possibility of occurring | [5 empty] | Significant psychological trauma | Multiple
[7 empty] | Significant | Minor injury or injuries from which recovery is not expected in the short term | Single
|  | Risk Acceptability | [5 empty] | Significant psychological trauma | Single
| 5 | Unacceptable level of risk | [5 empty] | Minor injury from which recovery is expected in the short term | Multiple
| 4 | Mandatory elimination of hazard or addition of control measure to reduce risk to an acceptable level | [5 empty] | Minor psychological upset; inconvenience | Multiple
| 3 | Undesirable level of risk. Attempts should be made to eliminate the hazard or implement control measures to reduce risk to an acceptable level. Shall only be acceptable when further risk reduction is impractical |  |  |  |  | Minor | Minor injury from which recovery is expected in the short term; minor psychological upset; inconvenience; any negligible severity | Single
| 2 | Acceptable where cost of further reduction outweighs benefits gained or where further risk reduction is impractical
| 1 | Acceptable, no further action required

## Sheet1
Control Type
Design
Test
Training
Process